## Sheet1
DocType_REV_ID | Entry Date | Review by | Detection version | Page/Line/Section/Entity | Open point: description of problem | Proposed Solution | Status
CRS_REVIEW_001 | 2022-11-16 | Esraa abdelnaby | V1.1 | 1//documentTitle | change the document Title | The document name shall be SAG ML Speech Recognition CRS | Closed
CRS_REVIEW_002 | 2022-11-16 | Esraa abdelnaby | V1.1 | [ Document Status , Document History , Reference Document, Project Description,System Context,CRS Requirements ] | The mentioned sections are not aligned together | all the document sections shall be aligned | Closed
CRS_REVIEW_003 | 2022-11-16 | Esraa abdelnaby | V1.1 | 1// Document Status | the Document Status is drafted | Document Status shall be proposed | Closed
CRS_REVIEW_004 | 2022-11-16 | Esraa abdelnaby | V1.1 | 2// Document History | the second change history in the Document History is not correct | the second change history in the Document History should map the review point id | Open
CRS_REVIEW_005 | 2022-11-16 | Esraa abdelnaby | V1.1 | 4 //system context | the model name , input and output signsls in the system context shall be edited | edit the model name , input and output signsls in the system context | Closed
CRS_REVIEW_006 | 2022-11-16 | Esraa abdelnaby | V1.1 | 4 and 5//CRSRequirements/descreption | the model name in the system context is not mentioned in the requirements descreption | add the model name mentioned in the system context to the descreptoin of the requirements | Closed
CRS_REVIEW_007 | 2022-11-16 | Esraa abdelnaby | V1.1 | 4 and 5//CRSRequirements/descreption | the Mel Spectrograms shall be mapped as inner signals | edit the Mel Spectrograms to INN_Mel_Spectrograms | Closed
CRS_REVIEW_008 | 2022-11-16 | Esraa abdelnaby | V1.1 | crs requiremnts | inner sginals are not clarified | you should add an info to clarify the inner signals | Closed
CRS_REVIEW_009 | 2022-11-16 | Esraa abdelnaby | V1.1 | req 3 | it is not suitable to state the architecture in the crs it should only exist in the archticture document | remove it | Closed
CRS_REVIEW_0010 | 2022-11-16 | Esraa abdelnaby | V1.1 | req 6 | the output signals doesn't match the existed one in the system context | The speech recognition class shall return the Output_Text_Command to ECU. | Closed
CRS_REVIEW_0011 | 2022-11-18 | Esraa abdelnaby | V1.2 | each section title and content | the format of the sections titles and content | edit them to be the same format | Open
CRS_REVIEW_0012 | 2022-11-18 | Esraa abdelnaby | V1.2 | 43//project descreption//definition | the definition shall be more descreptive | edit the definition | Open