## Sheet1
DocType_REV_ID | Entry Date | Review by | Detection version | Page/Line/Section/Entity | Open point: description of problem | Proposed Solution | Status
CRS_REVIEW_001 | 2022-11-12 | Esraa abdelnaby | V1.0 | 1//documentName | The document name shall be SAG ML modelName CRS | change Document Status to last Document History | Closed
CRS_REVIEW_002 | 2022-11-12 | Esraa abdelnaby | V1.0 | 1//documentHistory/change | The change shall not have repeated informations as (Add definition , Add features ,Add Key elements ,Add System Context) including in initial creation |  | Closed
CRS_REVIEW_003 | 2022-11-12 | Esraa abdelnaby | V1.0 | 2//projectDescription/definition | the definition shall describle only the feature which is mentioned in document name |  | Closed
CRS_REVIEW_004 | 2022-11-12 | Esraa abdelnaby | V1.0 | 2//projectDescription/keyElement | key element shall be as it is in CR document avoiding any details |  | Closed
CRS_REVIEW_005 | 2022-11-12 | Esraa abdelnaby | V1.0 | 3 and 4//CRSRequirements/covers | write the right requirement id from CR document |  | Closed
CRS_REVIEW_006 | 2022-11-15 | Esraa abdelnaby | V1.0 | all document | alignment not suitable | handle alignment | Closed
CRS_REVIEW_007 | 2022-11-15 | Esraa abdelnaby | V1.0 | all CRS requirements IDs are Wrong | swap between Req_ID and covers | handle alignment | Open
CRS_REVIEW_008 | 2022-11-15 | Esraa abdelnaby | V1.1 | 2//Reference Document/reference version | refernce version shall be 1.2 | handle alignment | Open
CRS_REVIEW_009 | 2022-11-15 | Esraa abdelnaby | V1.1 | 2//project description | Edit space between definition and features | handle alignment | Open
CRS_REVIEW_010 | 2022-11-15 | Esraa abdelnaby | V1.1 | 3//context diagram | Edit context diagram according to new signals names | handle alignment | Open